## Slide 1
Campaign Date
Reviews
Testing
High Level Tasks

## Slide 2: Wallops Ambient Light Radiometer & Ultraviolet Sensor Suite (WALRUSS) Sarah Roth – University of Wallops
IRAD
Fully characterizing the ultraviolet exposure of the balloon and associate materials in-flight will allow for a greater understanding of material degradation in-flight. This will help design materials to withstand ultra-long duration missions and decided if certain materials can be reused which will increase safety parameters and lower costs.
Build a custom sensor package that can fly as a piggyback on multiple missions. Sensor package should be able to be modified and allow for additional sensors. Data storage onboard and independent of all CSBF power/equipment.
April 2021
Drew is completing software design and testing
Final wiring schematic is in progress and final layout of hardware
Structural analysis packet is in progress
Additional purchases may be needed for hardware
Must allocate remaining funds by 5/1
Work Plan/ Quad Chart | 9/30/2020
Source ozone sensors/ solar power components | 9/30/2020
Software requirements delivered to 589 | 10/15/2021
Flight application submitted | 12/20/2021
Structural Analysis and Paperwork submitted to MM | 4/15/2021
Bench testing complete | 5/1/2021
T-Vac testing complete | 6/30/2021
Integration at Ft. Sumner | 8/1/2021
EXAMPLE